## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2025-04-29
Group Number |  | 16
Participant 1 |  | Andak Kadir Resul
Participant 2 |  | Liu Yueting
Participant 3 |  | Reithmaier Melanie
Participant 4 |  | Sabic Kenan
Participant 5 |  | Tekin Beyza
Mentor |  | Docsek Martin
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Punktsystem mit JavaScript und TypeScript | 3 | 3 | 0 | 1
2 | Grunddesign optimieren | 3 | 6 | 3 | 1
3 | Login / Registrierung mit der Datenbank verknüpfen | 3 | 6 | 3 |  |  | Teilweise passt
4 | Datenstruktur | 1 | 2 | 1 | 1
5 | Erstellung des DoDs und der User-Story-Akzeptanzkriterien | 2 | 1.5 | -0.5 | 1
6 | Kalender Komponent optimiert | 1 | 1 | 0 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol